## KPMAS T-UBT Scorecard BALT
KP Mid Atlantic Unit Based Team Scorecard - Baltimore Area Centers
UBT Leadership | UBT Workshop Date | Area of Focus |  |  | Creating T-UBT |  |  | T-UBT Activity |  |  |  | T-UBT Metrics / Progress to Goal
|  | Date Selected | Description | Value Compass / Regional Priority | Department Engaged as T-UBT | Date of Engagement Meeting | Request for RIM Date | RIM Training Date | Aim Statement | Date | PDSA Cycles started | Metric Used | T-UBT Target | Reg. Target | Current Performance
Towson | 2008-04-05 | 2008-05-10 | Improved notification of wait room delay | Best Service | Pediatrics | NA | 2008-06-10 | 2008-06-16 | To increase Patient Satisfaction with notification of waiting room delay in the Towson Peds department from 33% "Yes, was notified" in 1st QTR 2008 to 60% "Yes, was notified" by 3rd QTR 2008 | 2008-06-10 | 6/12/018 | PSAT: If you waited more than 15min in the waiting room, did a KP staff member inform you of the delay? (yes or no) | 60% Yes | NA | 33% 1st QTR 2008 50% 2nd QTR 2008 75% 3rd QTR 2008
|  | 2008-05-10 | Improved notification of wait room delay | Best Service | OBGYN | NA | 2008-07-29 | 2008-08-08 | Improve notification of waiting room delay in the OB/GYN department at Towson from 8% "Yes, was notified" on the 2nd quarter 2008 PSAT to 25% "Yes, was notified" on the 4th Quarter 2008 PSAT. | 2008-08-08 | TBD | PSAT: If you waited more than 15min in the waiting room, did a KP staff member inform you of the delay? (yes or no) | 25% Yes | NA | 8% 2nd QTR 2008 70% 3rd QTR 2008
Woodlawn | 2008-04-05 | 2008-06-25 | Improved focused diabetic elements of control | Best Quality | Int. Medicine | 2028-07-10 | 2008-07-10 | 2008-08-01 | Improve DM elements of care at the Woodlawn Center 3% points by the end of 4th QTR | 2008-08-01 | 2008-08-01 | Quality Reports: DM LDL Screening DM Lipid Lowering and ACE / Arb compliance | 3% increase | DM LDL: 86.4% DM ACE: 78.0% | DM LDL: 78% 1st QTR 2008 80% 2nd QTR 2008 84% 3rd QTR 2008 DM ACE: 35% 1st QTR 2008 43% 2nd QTR 2008 67% 3rd QTR 2008
White Marsh | 2008-04-05 | 2008-11-24 | Improved handling of MessageConnect Rx Refill | Best Service | Int. Medicine | 2008-12-11 | 2008-11-24 | 2008-12-11 | TUBT (12/11/08) |  |  | TBD | TBD | 95% | June-Nov = 91.6%
Severna Park | 2008-04-05 | 2008-09-09 | Improve Breast Cancer Screen Rates | Best Quality | GYN | TBD | TBD | 11/12 and 11/19 12:15pm - 1:00pm | To improve breast cancer screening rates from 74.29% in 3rd QTR to at least 81.3% by 2008 YE |  |  | Quality Reports: Breast Cancer Screening | 81.3% | 81.3% | 3rd QTR = 74.28%
City Plaza | 2008-04-05 | 2008-07-15 | Increase Colorectal Cancer screening rates | Best Quality | Center wide | 2008-08-18 | 2008-08-19 | 2008-08-21 | Increase the colorectal cancer screening of City Plaza patients, 50 years and older, by 3.07%, over the 2nd QTR 2008 results of 56.43%, by the end of 2008 | 2008-09-18 |  | Quality Reports: Colorectal Cancer Screening Rates | 59.5% | 59.5% | 2nd QTR 2008 = 56.43%
Annapolis | 2008-09-16 | 2008-09-16 | Improved message handling | Best Service/Message Connect | Center wide | 2008-10-21 | 2008-10-14 | 2008-10-21 | Increase Annapolis Medical Center’s Message Connect Compliance scores 1% point every two weeks, starting November 1st, to consistently meet or exceed the goal of 95%, as measured by the weekly Message Connect Compliance Report. |  |  | MessageConnect Report (weekly) | 95% | 95% | week of 10/17 = 93.9%
Col Gateway | 2008-07-12 | 2008-10-13 | My Health Manager enrollment | Best Service | Pediatrics | TBD | TBD |  | To increase Pediatric Patients enrolled in My Health Manager by 10% in one month (needs specific dates) |  |  | MyChart Statistics by Panel report (monthly) | 27% | NA | Aug = 31.1% Sept = 31.6% Oct = 18.3%
Note on A7: Kevin A Cornell: This center is part of Wave II Kaiser Permanente Performance Institute.

## KPMAS T-UBT Scorecard DCSM
KP Mid Atlantic Unit Based Team Scorecard - DCSM Centers
UBT Leadership | UBT Workshop Date | Area of Focus |  |  | Creating T-UBT |  |  | T-UBT Activity |  |  |  | T-UBT Metrics / Progress to Goal
|  | Date Selected | Description | Value Compass / Regional Priority | Department Engaged as T-UBT | Date of Engagement Meeting | Request for RIM Date | RIM Training Date | Aim Statement | Date | PDSA Cycles started | Metric Used | T-UBT Target | Reg. Target | Current Performance
Kensington | 2008-04-05 | 2008-04-05 | Integration of CSMP into UBT structure | Best Place to Work / Workplace Safety | Center wide | NA | N | varies | varies |  |  | WPS Injury Report | 15% reduction (57 Injuries) | 15% Reduction | See WPS Reports
|  | 2008-05-15 | Neurology Access Improvement | Best Service / Access to Spec. Care | Neurology | 2008-05-01 | 2008-05-15 | 2008-05-28 | To decrease the 2008 YTD avg. FTKA rate in the Kensington Neurology department from 13% in July 08 to 11.5% by 10/1/08 | 2008-08-01 | 2008-08-01 | FTKA Rate | 11.5% YTD | < 10% | 11.4% YTD 2008 as of October 24th, 2008
|  | NA | Increase enrollment of My Health Manager | Most Affordable / KPHC Realization | Center wide | NONE | N | TBD | Increase enrollment of Kensington Members with My Health Manager from 26% in 2007 to 35% by 12/31/08 (need to check this) | [5 empty] | 32.2% in Sept 32.6% in Oct.
Largo | 2008-04-05 | 2008-04-05 | Integration of CSMP into UBT structure | Best Place to Work / Workplace Safety | Center wide | NA | N | varies | 15% reduction in workplace employee injuries, as reflected in the Employee Injury Report, to be achieved during the period of September 2007 to September 2008 at the Largo Medical Center. |  |  | WPS Injury Report | 15% reduction (30 Injuries) | 15% Reduction | See WPS Reports
|  | 2008-09-25 | Medical Management Pilot (improved health outcomes in diabetics) | Best Quality / Affordable | Int Medicine | NA | 2008-09-25 | 10/28/08 and 11/14/08 | TBD
North Cap. | 2008-07-12 | 2008-10-10 | Patient Wait Experience | Best Service | Pediatrics | TBD | TBD | TBD | Increase the PSAT Exam Room Scores in the Peds Department from 68% to 85% by the end of Q1 – 09. |  |  | PSAT (Patient satisfaction with Wait Room Time) | 85% | 80% | 3rd QTR: 58%
Camp Springs | 2008-07-12 | NA | First Appointment of the Day | Best Service | Pediatrics | 2008-09-10 | 2008-09-19 | 10/13/2008 and 10/23/08 | To increase the % of 1st pts of the day checking in on time from 38.71% in Sept '08 to 60% by 12/31/08 in Peds at Camp Springs as reported by the regional First appointment of the day, start on time monthly report | 2008-10-23 | 2008-11-03 | FAD Report | 60% by 12/31/08 (1st appts of day checked in on time) | 80% of first appointments "started" within 5 minutes of appt. time | Sept = 38.71% Oct = 36.92%
West End | 2008-07-12 | 2008-10-03 | Patient Wait Experience | Best Service | OBGYN | 2008-10-16 | 2008-10-23 | 11/11/08 and 11/18/08 | To increase their exam room wait experience PSAT Scores from 53% to 80% by the end of Q1- 2009 | TBD | TBD | PSAT (Patient satisfaction with Wait Room Time, Comfort and notified of delay) | 80% | 80%
Marlow Heights | 2008-07-12 | NA | First Appointment of the Day | Best Service | Family Medicine | 2008-09-11 | 2008-09-19 | 2008-10-16 | TBD (12/12/08) | TBD | TBD | FAD Report | TBD | 80% of first appointments "started" within 5 minutes of appt. time | August = 53.9% Sept = 51.2% Oct = 39.7%
Prince George's | 2008-07-12 |  | Service - Improve the waiting room experience in OB/GYN | Best Service | OBGYN |  |  |  | Improve the PSAT score for wait room time in the OB/GYN department at the Prince George’s Medical Center, from 48% as the third quarter 2008 to 55% by the end of February 2009. |  |  | PSAT (Patient satisfaction with Wait Room Wait) | 55% by February 2009
Silver Spring | 2008-07-12 |  | Service - Improve the waiting room experience in Pediatrics | Best Service | Pediatrics |  |  |  | Improve the PSAT score in Pediatrics at the Silver Spring Medical Center from 56 % satisfaction with the wait room wait time (experience) to 59% by the end of January 2009. |  |  | PSAT (Patient satisfaction with Wait Room Wait) | 59% by end of January 2009
Shady Grove | 10/25/058 | 2008-11-14 | Improved Cervical Screening Cancer Rate | Best Quality | Family Medicine |  |  |  | TBD (12/10/08) |  |  | Quality Report | TBD | 83%
Gaithersburg | 2008-10-25 | 2008-10-31 | Improved Breast Cancer Screening Rates | Best Quality | Center wide | 2008-11-05 | 2008-10-31 | 2008-11-21 | TBD |  |  | Quality Report | TBD | 81.3% | 3rd QTR:78.48%
Germantown | 2008-10-25 | 2008-11-10 | Improved Patient Satisfaction for Exam room wait time | Best Service | Pediatrics | 2008-11-17 | 2008-11-10 | 2008-11-17 | TBD |  |  | PSAT (Patient satisfaction with Exam Room Wait) | TBD | 80% | 3rd QTR: 31%
Frederick | 2008-10-25 | 2008-11-05 | Controlling Hypertension | Best Quality | Int Medicine | 2008-11-19 | 2008-11-05 | 2008-11-19 | To reach Regional Goal of 56.70% of hypertensive patients with controlled Blood Pressure by end of 2nd Quarter 2009. |  |  | Quality Report | 56.7% | 56.7% | 3rd QTR: 52.32%
Note on A15: Kevin A Cornell: This center is part of the Kaiser Permanente Wave II Performance Institute

## KPMAS T-UBT Scorecard NOVA
KP Mid Atlantic Unit Based Team Scorecard - NOVA Centers
UBT Leadership | UBT Workshop Date | Date Selected | Description | Value Compass / Regional Priority | Department Engaged as T-UBT | Date of Engagement Meeting | Request for RIM Date | RIM Training Date | Aim Statement | Date | PDSA Cycles started | Metric Used | T-UBT Target | Reg. Target | Current Performance
Falls Church | 2008-05-17 | 2008-05-17 | Integration of CSMP into UBT structure | Best Place to Work / Workplace Safety | Center wide | 2008-09-22 | NA | CSMP Training completed/ RIM training TBD | varies |  |  | WPS Injury Report | 15% reduction (42 Injuries) | 15% Reduction | 2007 - 49 Injuries Per. Year 2008 Annualized (as of 2/29/08) 26
Springfield | 2008-05-17 | 2008-05-17 | Integration of CSMP into UBT structure | Best Place to Work / Workplace Safety | Center wide | NA | NA | varies | varies |  |  | WPS Injury Report | 15% reduction (28 Injuries) | 15% Reduction | 2007 - 33 Injuries Per. Year 2008 Annualized (as of 2/29/08) 26
|  | 2008-09-23 | On Start Time/FAD | Best Service | OB-GYN | 2008-10-23 | 2008-10-23 | 2008-11-11 | The Springfield OB/GYN team will increase their percentage of patients checkd in on time and roomed on time to 60% or greater by March 1st, 2009 for all 1st Appointments of the Day
Manassas | 2008-05-17 | 2008-09-10 | First Appointment of the Day | Best Service | OBGYN | 2008-10-16 | 2008-10-20 | 2008-10-20 | The Manassas OB/GYN team will have 80% of 1st appointments of the day room on time by 11/30/08. |  |  | FAD/Self Collected Data | 60% | 80% | Aug 2008 = 44% Sept 2008 = 73% Oct 2008 = 69%
Woodbridge | 2008-05-17 | 2008-08-20 | Code Response Team | Best Quality | Center wide | 2008-09-17 | 2008-09-02 | 2008-09-17 | Ensure that in any instance in which a person is found in distress in or on the grounds of the Woodbridge Medical Center there is an appropriate response within x minutes (or seconds). | 2008-09-17 | TBD | TBD | TBD | TBD
Burke | 2008-05-17 | 2008-08-14 | First Appointment of the Day (clinic start on time) | Best Service | Family Practice | 2008-09-03 | 2008-08-14 | 2008-09-10 | Meet or Exceed 80% target for 1st Appointment of the day start on time in the Burke Family Medicine Department by 10/31/08 | 2008-09-03 | 2008-09-03 | FAD/Self Collected Data | 80% | 80% | Aug 2008 - 48% Sept 2008 - 75% Oct 2008 - 86%
Fair Oaks | 2008-10-04 | 2008-10-31 | Increased Mammography Screening Rates | Best Quality | Center wide | 2008-11-03 | 2008-10-31 | TBD | To increase the mammography screening rate for Fair Oaks Medical Center female population 52-69 years of age from 79.2% to 81.30% or better by March 30, 2009 |  |  | Clinical Quality Report | 81.3% | 81.3% | 3rd QTR - 79.61%
Loudon / Ashburn | 2008-10-04 | 2008-10-31 | Improved Waiting room experience | Best Service | Center wide |  |  |  | Ashburn IM-Peds will improve satisfaction with wait room wait to 68% or better by January 31st, 2009. |  |  | PSAT (Patient satisfaction with wait area wait, Question 12d) | 68% | 68%
Reston | 2008-10-04 | 2008-10-31 | Improved Waiting room experience | Best Service | Internal Medicine | 2008-11-07 | 2008-10-31 | 2008-11-11 | Reston IM team 2 will improve patient satisfaction with wait room wait to 64% or better by January 31st, 2009. | 2008-11-11 | TBD | PSAT (Patient satisfaction with wait area wait, Question 12d) | 64% Very Satisfied | 64% Very Satisfied | IM Team 2 2nd QTR PSAT: 67% Very Satisfied IM Team 2 3rd QTR PSAT: 60% Very Satisfied
Penderbrook | 2008-10-04 | 2008-10-23
,
Note on A9: Kevin A Cornell: This center has is part of the Kaiser Permanente Wave II Performance Institute

## KPMAS R-UBT Scorecard
KP Mid Atlantic Unit Based Team Scorecard
UBT Leadership | Date Selected | Description | Value Compass / Regional Priority | Department Engaged as T-UBT | Date of Engagement Meeting | Request for RIM Date | RIM Training Date | Aim Statement | Date | PDSA Cycles started | Metric Used | T-UBT Target | Reg. Target | Current Performance
Clinical Call Center | 2008-05-01 | Attendance - UA's | Best Place to Work/ Best Service | 2008-05-01 | NA | NA | 2008-06-25 | To improve attendance at the Clinical Call Center by reducing the overal UA's by 15% from the 1st/2nd QTR Avg of 171.3 per pay period to 145.51 per pay period by end of 3rd QTR 2008 | 2008-06-25 | 2008-06-08 | Call Center Attendance Report | 145.51 Avg UA's per pay period | NA | 3rd QTR = 135.67 UA per pay period